
[image: image1.jpg]=™ MODEL WATERSHED





Watershed Enhancement Project Proposal

1.
Project Name:  Catherine Creek-44 Stream and Fish Habitat Restoration 
2.
Applicant:   Union Soil and Water Conservation District



       Ag Service Center, Room 7



       10507 North McAlister Road



       La Grande, Oregon  97850



       unionswcd@hotmail.com


       541-963-1313 (office)



       541-963-1075 (fax)

3.
Participating Landowner(s) and Agencies: 




      Smith Family Trust, Landowner

                1817 SW 45th, Pendleton, OR  97801



    Douglas Kinsley, Landowner

                            60026 Hwy. 203, Union, OR  97883
                            Robert Richards, Landowner

                            P.O. Box 536, Union, OR  97883

                            Ken Fite, Landowner
                            P.O. Box 518, Union, Oregon  97883

                            Bert Kirby, Landowner
                            58869 Hwy 203, Union, Oregon  97883



    Ralph Eyre, Southern Cross LTD, Landowner
                            P.O. Box 567, Union, OR  97883

                            Oregon Department of Transportation

                            3012 Island Ave.
                            La Grande, OR  97850


                         Oregon Department of Fish and Wildlife

                            107 20th St., La Grande, Oregon  97850

    541-962-1837

    winston.h.morton@state.or.us



Confederated Tribes of the Umatilla Indian Reservation




10507 N. McAlister Rd, Room 2, La Grande, Oregon  97850

                     541-969-3142

                      allenchilds@ctuir.org



US Bureau of Reclamation




Ag Service Center, Rm. 4


      
10507 North McAlister Road



       La Grande, Oregon  97850



      
ddyke@usbr.gov

      




541-963-1313 (office)



      
541-963-1075 (fax)

4.
Project Contact(s):   Technical:   Darrell Dyke






                                   US Bureau of Reclamation



                                   Ag Service Center, Room 4


      
                                   10507 North McAlister Road



                                           La Grande, Oregon  97850



      
                                   ddyke@usbr.gov

      




                                   541-963-1313 (office)



      
                                   541-963-1075 (fax)


Administrative:                            Craig Schellsmidt




                                         Union Soil and Water Conservation District



                                         Ag Service Center, Room 7



                                         10507 North McAlister Road



                                         La Grande, Oregon  97850



                                         unionswcd@hotmail.com


                                         541-963-1313 (office)



                                         541-963-1075 (fax)
5.
Project Location: 

The proposed project is located approximately 4 miles Southwest of Union, Oregon on Catherine Creek in the Upper Grande Ronde Subbasin.  The project legal description is:  Section 34 Township 4 South, Range 40 East WM, and Section 3, Township 5 South, Range 40 East WM.  The project is located on private land.

Long Range Project Reach Overview:

This multi-phase project’s goals and objectives are stages in an overall large scale local partnership effort between 6 private landowners and the USWCD, BOR, CTUIR, and ODFW.  The total project area encompasses approximately 4 miles between R.M. 42 and 46.  Since spring 2010, these partners have been working to strategize, plan, and design a multi-faceted and phased project addressing critical Spring/Summer Chinook habitat limiting factors to promote increased capacity for spawning, summer rearing, and overwintering habitat within the Middle Catherine Creek Reach.  A Rapid Site Assessment completed in 2011 by BOR and several site visits from project partners indicated that significant opportunities exist to improve habitat conditions and address limiting factors throughout the project area.  The project has been broken down into 3 remaining phases allowing for funding and a feasible construction schedule.  Phase I, funded in 2013, is currently under construction with the remaining 3 phases included in this proposal.  Project phases include a variety of habitat enhancement and restoration strategies including: 

· Irrigation Point of Diversion (POD) consolidations, removal of 4 seasonal push-up dams, and establishment of water conservation measures such as irrigation delivery pipelines, off-channel watering systems, riparian plantings, and riparian exclosure easement fences.  
· Re-meandering channel segments.
· Re-activation of historic channel segments.
· Construction/re-activation of side channels and alcove habitat.
· Reclamation of channelized reaches into complex side channel and wetland habitat. 
· Removal and relocation of berms to promote floodplain connectivity.
· Installation of Large Wood Material (LWM) structures and riffle complexes.
· Riparian plantings and seeding.
· Secure conservation easements with landowners to ensure the long term protection and success of the project. 
Phase II - FY 2014 Current Proposed Phase is located at the furthest upstream location encompassing R.M44.8 - 45.9 and includes the following:
· Construction of a consolidated diversion structure combining 4 existing points of diversion into a single structure and fish screen. 
·  Installation of LWM structures to initiate pool formation and shade cover.

· Construction of an irrigation piping network on the north and south sides of Catherine Creek, improving efficiency for delivery of legal water rights. 

· Side channel and alcove construction.

· Riffle-run-pool creation. 
· Increased floodplain connectivity.

· Establishment of an enhanced riparian corridor through riparian plantings. 
Phase III - FY 2015 is located in the middle of the project encompassing

  R.M 44.1 - 44.8 and includes the following:
· Increase floodplain connectivity; enhance channel meanders, and side channels. 
· Installation of LWM structures.

· Side channel and alcove construction.

· Riffle-run-pool creation.

· Channel re-alignment. 
· Establishment of an enhanced riparian corridor through riparian plantings.    

Phase IV - FY 2016 is located at the downstream end of the project encompassing R.M 42.8 - 43.3 and includes the following:
· Establishment of riparian corridor.
· Enhanced floodplain connectivity. 
· Installation of LWM structures.
· Construction and or activation of side channels and an alcove.
· Riffle-run-pool creation.
· Increase floodplain connectivity and off channel habitat. 
· Installation of earthen berms to protect stream adjacent outbuildings from flood events. 

6.
Project Objectives:   

Primary habitat limiting factors identified within the project area have been developed through literature review, field visits by Basin biologists, and field investigations and reference of the NOAA Fisheries NE Oregon Snake River Recovery Plan and BiOp Expert Panel Process commissioned by BOR and BPA.  Key habitat limiting factors to be addressed include:

	CCC3 and UGS10A - Middle Catherine Creek 

(Pyles Creek To North and South Forks of Catherine Creek)

	1.1: Habitat Quantity:  Anthropogenic barriers.

	4.1: Riparian Condition:  Degraded riparian conditions.

	4.2: Riparian Condition:  Large wood Recruitment.

	5.1: Peripheral and Transitional Habitats:  Side channel and wetland conditions.

	5.2: Peripheral and Transitional Habitats:  Floodplain condition.

	6.1: Channel Structure and Form:  Bed and channel form.

	6.2: Channel Structure and Form:  In stream structural complexity.

	7.2: Sediment Conditions:  Increased sediment quantity/excess fine sediment.

	8.1: Water Quality:  Temperature, elevated summer stream temperatures, low DO levels.

	9.2: Water Quantity:  Decreased water quantity, lower summer flows.


Project Goal Statement:
The overall project goal is to restore natural channel functions and processes that provide increased capacity to spawn and rear ESA listed Salmon and Steelhead while protecting and maintaining the utility and economic viability of working ranches.  The project objectives are to protect habitat, enhance floodplain connectivity, in-stream structural diversity and complexity, and riparian habitat conditions assisting Salmon/Steelhead recovery.  Project activities reduce excessive bank erosion, heavy sediment loads, and high summer water temperatures, while creating and or enhancing complex fish habitat, especially large wood structures, and increasing riparian vegetation. Consequently, these limiting factors for Spring/Summer Chinook, Steelhead, and Bull trout in the Upper Grande Ronde/Catherine Creek Subbasin will be addressed.  
7.   Project Description:
The project area is located within Reach UGS10A (Summer Steelhead) and Reach CCC3 (Spring-Summer Chinook) (Northeast Oregon Snake River Recovery Plan, Draft (NOAA, March 2012) and BiOp Expert Panel Draft Reach Delineations (BPA/BOR, April 2012). Geographically, these reaches encompass Middle Catherine Creek from the confluence of Pyles Creek upstream to the North and South Forks of Catherine Creek.  The Project Area is also located within Reach 4 of the Bureau of Reclamation Tributary Assessment (BOR, February 2012) and has been identified as one of the highest priority reaches for restoration actions.  BOR and ODFW assessments found Catherine Creek within this project area to include stream bank instability, high channel width/depth ratios, poor riparian vegetation, lack of side channel habitat and floodplain connectivity, and poor in-channel diversity and complexity within individual reaches. Additionally, the project reach is affected by winter icing, high summer water temperatures, and low summer base flow.  

The 2014-2016 phases propose consolidation of 4 irrigation points of diversion into a single point of diversion, construction of an irrigation delivery pipeline network from the consolidated diversion, and 3 miles of riparian corridor and in-stream enhancement through side channel construction, floodplain connectivity, in-stream complexity, and riparian vegetation plantings.
Existing Conditions: 

Environmental baseline conditions were derived from various sources including baseline field surveys, site aerial photography, LiDAR imagery, habitat characterization reports, and communication with the landowners and partnership agency staff with knowledge of the action area.  Project partners have worked together to compile datasets and develop baseline assessment data with an accompanying hydraulic model and a 100-year flood event model.  Additional limiting factors and existing conditions’ data were compiled from ODFW habitat surveys and from the BOR Catherine Creek Tributary Assessment and BiOp expert panel draft recovery plan. Tetra Tech completed a Wetland Delineation Report in September 2013 for phases II, III, and IV. 

The existing channel is relatively homogenous with minimal habitat availability and complexity.  Current ODFW fish monitoring and BOR assessment confirms this project site is a high priority critical area for juvenile Chinook Salmon over-wintering habitat, spawning, and summer rearing.  During the winters of 2009-2012 the ODFW fish tracking study of over-wintering juveniles in the area showed a preference for deeper pools with cover habitat (overhanging vegetation and/or submerged LWM).  There is a lack of LWM which has reduced the available cover habitat and ability to sustain deep pools.  In addition, high summer water temperatures are common during the irrigation season.

Generally, the project Reach is in poor to fair condition with stream segments exhibiting a lack of deep pools, little complex cover, channel incision, and poor riparian vegetation communities with some large trees and little overhanging vegetation.  Prior channelization has removed the meander bends and point bars that are essential to create and maintain deep pools.  Sediment storage in the channel has caused severe localized bank erosion and over-widening.  The channel is becoming shallower which further exacerbates many of the problems already present in the area.  Stream bank erosion is prominent along many portions of the project area which actively erode stream banks and contribute excessive sediment into Catherine Creek.  Channelization and past intensive streamside livestock grazing practices have led to high channel width/depth ratios, loss and suppression of riparian vegetation, subsequent loss of future channel complexity, and stream bank erosion leading to excessive fine sediment loads in the channel.  The project complements completed and on-going fish habitat enhancement activities in the Catherine Creek watershed.  Overall project goals, objectives, and limiting factors include:
[image: image2.jpg]|Snake Riwer

Basi Drat
BOP [Recoery =2 e
Pl Name| Stmams | e 1o nen | A=seesment | [§ GneeNEion B s o miop | Cone P oject Goals P oject Objectives FRkmet e rtomg Netics
Uit stehead | Uni hiook | Touchstones | (0718 [ESREEE. | subcar 12000 Actonsiletrcs
)
Liniting
Factors
Improse diersion
Bicts- L et 14 [anthopogenic | stuctures S ubbasin Plan
Connectity Quantiy Barers Reference: Channel
Canditons. (page 260)
Protect Hatitat Subbasin | "ot ablat: Dewlop
et Satbeet |rparian casement vith 8
&1 [Riparn Candtion | Protectn fage 258) |10
¢ ¢ (CTURIBPAIODFI easement
Riparian L [Riprian andior CREP) —
Vegetation Canditon E nhance rparan hatat [Enhance riparian habitat Floodplain
conditons. Subbasin Plan [conditions: ncrease rpanan Comeciviy
Refrence: Riparan |Plant communies through Bl
42 |LWDRecuiment | congiions (page anting and seeding and Poson ore
e O sl
—— Enhance Floodplain inciudes: 2mites (P50
el | gq P Eonance Fosap_[Connectivy:Remor chama st e
- comectity | 5 ¢ Conditions o Sbas P nhance In.sream stuctural chamelhabiat, 55 oo
e Kl . [Foctpan Condiions (bage iversity and complexity: Re il habtat P
£2 :

ol Condtion actiate historc chamnel [complxity. g
Ml —Fsdwd el meander to ncrease sinuosity|Remoral of b i
Popa |Caemne| 201 agn 83 o and place arge wood within  migaton push up | * g

Projectin | Creek | 217 Channd Enhance natream  |actie chamel dams () A
o o v stnctural duersiy and | Reduce excessive ssdiment Planing wiin | o SO
pea i o |l compleity. Subbasin Plan |l anage riparian grazing vith |rparian area S
i Retrance: Chamel  [exclusion eces,stabiizs ~|Seeding disuted | =TS0 208,
Seomomhelesy Canditons (page oxistng emsion stes with [ground. il
wood stnuctures and &= [Constructrparian pori- g
ccie  |sstablshmentofegetation.  [fnce
sedment st | st Subsan pn pecram mmerpeak [ofcamnlvatr | DECTE% amner
e 12 temperatures o be developed |/ (eTPeraires
anditons Sedment Quanty|  Rerence: Seciment [1STP ved [y atrtempenture -
Condtons page 261), | mprovlincrease wegeatic oo mmehe.
cowershade to decrease B
summer stream temperatures Aok Mo
Decrease summer peak[ind increase winter i s
Water L temperatures. Subbasin ['enperiures
& |auaity &1 |Temperue Plan Refrence: Ripanan |Decreased Water Quanity;
Condifons (page 252). |Consoldste points of iversion
Purchase water rghts
Hydrology
Increase summer vater
o watr o [Decreased Water | quantiy. Subbasin Plan
7 |ouanity %2 Jauantity Reference: LowFlow

Conditons (page 263}






Specific Actions 
A. Consolidated Diversion and Intake Structure, Phase II, FY 2014: 
Construction of a consolidated roughened channel diversion structure and fish screen located between RM 44.75 – RM 44.85.  This diversion design promotes natural river processes, allows fish passage for all life stages, removes 4 annual push up dams, consolidates 4 PODs into 1, and greatly reduces management actions needed by the landowners in order to access their legal water rights.  This portion of the channel is currently over-widened and will require fill material to reduce the channel width to ensure establishment of channel hydraulics, which will also maintain the diversion.  LWM structures installed upstream of the consolidated diversion structure as part of Phase I in Fall, 2013 are expected to initiate formation of a pool at the desired diversion intake location.  
B.  Irrigation Pipeline, Phase II, FY 2014:
Construction of an irrigation piping network located on the north and south sides of Catherine Creek.  The north pipeline will extend approximately 8,600 feet and will begin just downstream of the existing fish screen and will follow an existing ditch line along the toe of the hillside. The north side pipeline will be supplied by the consolidated diversion, and the south side pipeline will be supplied by an existing screened diversion near RM 45. The south pipeline will extend approximately 3,000 feet and follow existing ditch alignment. There are no plans to improve the south side existing diversion structure or fish screen.  However the habitat design in this area will include maintaining the functionality of the existing diversion.  Both pipelines will have multiple laterals or sprinkler systems extending toward Catherine Creek to provide irrigation water to adjacent pastures.  NRCS is currently working with 3 landowners to convert existing irrigation systems from flood to sprinkler of which they will engineer and design. Remaining existing ditches will be decommissioned, filled and seeded.  The pipelines will increase irrigation efficiency by eliminating the need for “carry water” due to seepage loss and roughness associated with open channel flow in ditches.  
C.  Habitat: 
1.  Phase II, FY 2014, R.M 44.8-45.9:
Four side channels will be constructed within this project reach to provide off-channel habitat during a wide range of flows up to a 100 year flood event.  Additional habitat enhancement efforts include 
· Installation of 40 LWM structures
· Construction of 1 backwater alcove to provide juvenile Salmonid refuge and connection to an adjacent spring supplying colder water during low flow season.
· Removal of 1 riprap berm, restructuring of over-widened and eroded banks and a low elevation bench to promote vegetative growth.
· Creation of 2 earthen berms totaling 1,266 feet in length with a 8 foot top width to provide flood protection of stream adjacent outbuildings.
· Boulder placement to induce ice break-up during winter months and provide bank and an existing bridge protection from erosion during high flow events.
·  Installation a hardened livestock crossing.
2.  Phase III, FY 2015, R.M 44.1-44.8: 
Efforts within this reach will focus on installation of LWM structures, side channel or alcove construction, and creation of riffle-run-pool channel form elements.  Project metrics include:
· Installation of 55 wood complexes.

· 2,747’ of side channel creation and 300’ of new channel creation. 

· Creation of 4 new back water alcoves.

· Installation of 2 new boulder complexes.

· Creation of 10 new riffles complexes.

· Riparian planting of 2,100 container plants.

3.  Phase IV, FY 2016, R.M 42.8-44.1: 
Efforts within this reach will focus on in-stream habitat elements, floodplain connection, enhanced channel meanders and side channels. At R.M 43.3, work will include abandonment of an existing diversion structure.  This diversion will 
be re-located to the consolidated diversion to be constructed at R.M 44.8.

Specific restoration efforts include: 

· Installation of 103 wood complexes.

· 4,279’ of side channel creation and 1,500’ of new channel creation.

· Creation of 4 new back water alcoves.

· Installation of 8 new boulder complexes.

· Creation of new riffle complexes. 

· Riparian planting of 6,292 container plants.
Riparian Planting: The following is a general strategy to promote and restore riparian vegetation within each of the project phases:
Re-seed and Re-plant Disturbed Areas.

· Using a combination of live stakes, plugs, and container plants all disturbed areas during construction will be re-seeded using native seed mixes and plants. The establishment of a healthy, self-sustaining native vegetative community throughout the project site is vital to the success of a stream enhancement project.  Re-vegetation immediately after grading provides key initial site stabilization and energy dissipation.  Such communities promote short-term and long-term bank stabilization, shade for cooler water, protective cover for fish, habitat for terrestrial wildlife (birds, mammals, amphibians, and macro invertebrates), and future wood material recruitment.
The riparian planting plan will be based on an inventory of site plan species, existing and proposed site topography and expected hydrology.  The zones include:

·   Area 1 – This area will support willow stake plantings along low banks, benches, and side channels.  These areas are above the ordinary high water mark but are expected to typically inundate or saturate on an annual basis.

· Area 2 – This area is located in lower floodplain and wetland areas that currently support wetland plant communities.  The plantings will include Willow stakes and additional wetland shrub species adapted to wetland hydrology.

·   Area 3 – This area is located on upper floodplain terrace areas.  These areas are not typically inundated and will likely require irrigation to get the shrub and tree plantings established.

Approximately 17 acres of the project area are currently enrolled in a Conservation Reserve Enhancement Program (CREP) program and have been fenced to exclude livestock.  Although the remaining project area is not presently enrolled in any easement programs, currently there is fencing along Catherine Creek throughout the entire project reach.  However, as remaining phases of this project are completed, additional exclusion fencing and conservation easements will encompass the entire project area. 

Trap and haul (salvage) fish and other aquatic species from construction areas to avoid any unintentional take or injury.
· All fish capture, handling, and relocation would be directed by qualified and experienced fish biologists in accordance with NMFS, USFWS, and ODFW fish removal protocol with guidelines.
 Benefits

The project complements completed and on-going fish habitat enhancement activities in the Catherine Creek watershed.  The project area is within historic ESA listed Salmonid high priority spawning, rearing, and over-wintering habitat.  ODFW fish monitoring and BOR Tributary Assessment studies indicate a lack of in-stream complexity and fish habitat, particularly in the Middle Catherine Creek reach area from the confluence of Pyles Creek upstream to the North and South Forks of Catherine Creek.   The completed project area will further sustain Steelhead, Chinook and Bull trout, as well as other species.  Specific project benefits include:
· Potential increased summer base flow conditions and decreased summer high water temperatures.

· Increased winter temperatures with increased hyporheic connectivity and improved riparian and floodplain conditions.

· Improved/restored floodplain connectivity and natural channel morphology with stable channel form.

· Improved distribution and sorting of sediment and potentially increased sediment storage at controlled locations.
· Increased/reconnected side channels and alcove habitat.

· Improved channel dimension, pattern, and profile with decreased width/depth ratios, increased sinuosity, and decreased channel slope.

· Engineered LWM structures will maintain the desired channel configuration and increase in-stream habitat complexity.

· Increased in-channel complexity and diversity with a distribution of large pools, glides, runs, and riffles of various sizes and complexity.
· Improved year-round fish passage through removal of 4 annual push-up dams.
· Long-term increase LWM recruitment from near non-existent conditions through re-vegetation of native Willow, Cottonwood, Alder, shrubs and grass plantings.  The additional vegetation will also add stability to stream banks and decrease erosion and sediment loads into the Creek.

· Riparian plantings and exclosure riparian fencing will increase wildlife habitat created within the project area. 
· Decreased landowners’ maintenance of irrigation devices and screens and decreased risk to juvenile stranding in irrigation ditches.
· Conservation easements will protect the project and allow it to mature.

Project Maintenance 

USWCD, CTUIR, ODFW staff, and the landowners will maintain the project.  Extensive maintenance of in-stream habitat enhancement structures and exclosure fencing is not anticipated.  Maintenance associated with the conservation easements includes annual fence inspection, repair and maintenance of planted materials consisting of managing competing vegetation to increase plant survival rates.  A weed management plan will be developed and implemented once Phase II of the project is completed and will expand upon completion of each subsequent phase. 
Permits 
Project partner staffs are completing all environmental compliance requirements in cooperation with BPA staff.  These requirements include NEPA, ESA Section 106 consultations, and Oregon DSL and USCOE Fill Remove and Wetland Mitigation permit authorizations.  BOR conducted a cultural resources survey in the summer/winter of 2012.  Currently, the Section 106 consultation is in progress and the permit applications will be submitted for phases II-IV in November 2013.
Monitoring Plan 
Photo points will be established in 2013/2014 by the USWCD and partnership agency staff to provide comparative progress of implementation success and habitat complexity.  A final report will be submitted by the USWCD to document the actual project implementation and will include the established photo points featuring pre and post construction implementation.  All required monitoring reports will be submitted to the appropriate funding and permitting agencies.  A monitoring plan has been developed to evaluate project objectives which include periodic visits to photo points. Surveys of monumented cross-sections established by Anderson Perry and BOR in 2011 will be conducted to monitor channel processes. 
Work Dates 
Project in-stream construction will begin before and coincide each year with the in-water work window, July 1st to August 15th, as recommended in Oregon Guidelines for Timing of In-Water Work To Protect Fish and Wildlife Resources, published by ODFW June, 2008.  Specific dates for Phase II and subsequent project aspects include: 
·   Habitat, Hydrologic, Geomorphic Survey/Analysis:  Summer/Fall/Winter 2013/2014. 

·   Pre-design completed:  Fall/Winter 2014. 

·   Permitting/Consultations:  Winter/Spring 2014/2015. 

·   Final design completed:  Spring 2014. 

·   Construction:  Summer/Fall 2014. 

·   Monitoring:  Initiated in 2012 and will continue through 2022. 
*Note:  All items prior to construction, while essential for the project are not being sought for funding.  All monies requested for funding are for construction and project management during construction.
8.  Project Budget

A detailed budget for each proposed project area as well as an overall multi-phase budget with information for materials, labor costs, work units, and cost share by funding source is provided.  BPA funds will be utilized for construction and materials. Project management funding is only sought for during construction to manage and inspect the project area, coordinate schedules, solicit bids, develop and award contracts, monitor project post construction, obtain all necessary invoices, and produce all required construction forms and reports.  The budget estimate was developed using costs from previous stream restoration projects as well as current R.S. Mean’s costs.  Unless otherwise noted the unit costs reflect the costs to purchase, transport, and place materials.
Multiple Union SWCD past project budgets, experience, and conversations with contractors, suppliers, and partnership agency’s staff provided information to develop an accurate project budget.  Project management is based on the District’s experience with other projects and the amount of staff time it takes to complete large wood structure stream restoration projects.
Pipeline, Phase II, FY 2014*

[image: image3.emf]Qty Description Unit Materials Labor Total Incl. O&P Cost

1 Mob and Demobilization LS $22,353.52

1 Clear and grub LS $4,000.00 $4,000.00

500 15" PVC-PIP L.F. $10.60 $4.20 $14.80 $7,400.00

6440 10" PVC-PIP L.F. $4.70 $3.50 $8.20 $52,808.00

1102 8" PVC-PIP L.F. $3.00 $2.00 $5.00 $5,510.00

3495 6" PVC-PIP L.F. $1.70 $1.00 $2.70 $9,436.50

3219 4" PVC-PIP L.F. $0.80 $0.50 $1.30 $4,184.70

7500 Excavation & Backfill C.Y. $9.60 $2.40 $12.00 $90,000.00

550Select Backfill for Pipe Bedding C.Y. $33.60 $8.40 $42.00 $23,100.00

5 4" Farm Delivery Ea. $2,000.00 $1,500.00 $3,500.00 $17,500.00

23 Turnouts (Alfalfa Valve) Ea. $120.00 $30.00 $150.00 $3,450.00

2 Turbulent Fountain Screen Ea. $1,947.00 $1,126.00 $3,073.00 $6,146.00

$245,888.72

Unlisted Items 10% $24,588.87

$270,477.59

$270,500.00

Total for listed items

Total for Schedule

TOTAL CONSTRUCTION COST


*Note: Unlisted Items Definition:

This cost represents the recognition that all features and individual items that may be necessary to bring this project to completion have not yet been identified.  For this project, unlisted items may include, but are not limited to, items such as; O & M roads, re-vegetation measures, road and crossings, pipe thrust blocks, expansion joints and tee connections to existing pipes or structures.

NRCS Cost Share for On-Farm Improvements: The following is an estimate of converting 3 landowners from flood to sprinkler irrigation within the project area, FY 2014:
	Item
	NRCS contribution
	Proposed BPA funding
	Total Cost

	Electric Pumps
	$17,579
	
	$35,158

	Irrigation Water Management
	$3,130
	
	$6,260

	Sprinklers
	$42,504
	
	$85,008

	Pipeline
	$80,275
	$48,165 *
	$128,440

	Total On-Farm Improvement Cost
	
	
	$254,866


*This figure is included in the above pipeline budget. Additional cost share funding to cover on-farm improvements will be sought from other funding sources. 
Consolidated Diversion and Intake Structure Phase II, FY 2014:
	No.
	Description
	Unit
	Estimated Quantity
	Material Unit Price
	Labor Unit Price
	Total Cost

	1
	Mobilization
	LS
	All Req’d
	-
	$10,150
	$10,150

	2
	Clearing, Grubbing
	HR
	10
	-
	280
	2,800

	3
	River Left Channel modifications
	HR
	90
	-
	280
	25,200

	
	Fill*
	CY
	1,800
	-
	-
	-

	
	Wood Material
	EA
	30
	300
	
	9,000

	
	Coconut Mesh
	SY
	450
	3
	
	1,350

	
	Plantings*
	LS
	All Req’d
	-
	4,000
	4,000

	4
	Roughened Channel
	HR
	80
	-
	280
	22,400

	
	Streambed Simulation Material
	EA
	500
	25
	-
	12,500

	
	Rock
	CY
	80
	30
	-
	2,400

	5
	LWM Structures (1)
	HR
	30
	-
	280
	8,400

	
	Root Wads
	EA
	22
	300
	-
	6,600

	
	Racking Material
	EA
	6
	100
	-
	600

	
	Rock
	CY
	80
	30
	-
	2,400

	
	Plantings*
	LS
	All Req’d
	-
	1,500
	1,500

	6
	Small Wood Habitat Structures (2)
	HR
	30
	-
	280
	8,400

	
	Root Wads
	EA
	14
	300
	-
	4,200

	
	Rock
	CY
	60
	30
	-
	1,800

	
	Plantings*
	LS
	All Req’d
	-
	1,000
	1,000

	7
	Woody Debris Structures (6)
	HR
	30
	-
	280
	8,400

	
	Root Wads
	EA
	24
	300
	-
	7,200

	
	Rock
	CY
	60
	30
	-
	1,800

	
	Plantings*
	LS
	All Req’d
	-
	1,500
	1,500

	8
	Diversion Intake Structure
	HR
	100
	-
	250
	25,000

	
	Concrete
	CY
	30
	120
	-
	3,600

	
	Headgate/Walkway
	LS
	All Req’d
	7,000
	-
	7,000

	
	Rock/Streambed Materials
	CY
	30
	30
	-
	900

	9
	Irrigation Ditch Improvements
	HR
	30
	-
	280
	8,400

	
	Streambed Materials
	CY
	20
	25
	-
	500

	10
	Site Restoration (seeding, cleanup)
	LS
	All Req’d
	1,500
	2,500
	4,000

	11
	Water Control
	LS
	All Req’d
	-
	12,000
	12,000

	
	Total 2013 Estimated Construction Cost
	
	
	
	
	$205,000


*Assumes these items can be acquired near the project sit at no material cost to the contractor.
Proposed Habitat Work, R.M 44.8-45.9, Phase II, FY 2104 
	Landowner
	Section
	River Mile
	
	

	
	Parcel 5

Parcel 6
	RM 44.8 to RM 45.3

RM 45.3 to RM 45.9


	
	

	Habitat work on this section includes: construction of 4 side channels, construction of a back water alcove, bank stabilization, installation of LWM structures, boulder placement, removal and relocation of berms, and water gap and bridge stabilization.


	Item #
	Item Description
	Units
	Unit Cost
	Quantity
	Cost

	1
	Mobilization and Demobilization


	Lump Sum
	$30,000
	1
	$30,000

	2
	Environmental Controls (SWPPP, ESC, Ets.)
	Lump Sum
	$3,600
	1
	$3,600

	3
	Cofferdams, Dewatering and Water Management
	Lump Sum
	$36,000
	1
	$36,000

	4
	Temporary Haul Road
	Lump Sum
	$3,600
	1
	$3,600

	5
	Side Channel 1
	CY
	$11.40
	709
	$8,083

	6
	Side Channel 2
	CY
	$11.40
	260
	$2,964

	7
	Side Channel 3
	CY
	$11.40
	904
	$10,306

	8
	Side Channel 4
	CY
	$11.40
	593
	$6,760

	9
	Alcove 
	CY
	$11.40
	108
	$1,231

	10
	Landscape Berm 1
	CY
	$12.00
	662
	$7,944

	11
	Landscape Berm 2
	CY
	$12.00
	1083
	$12,996

	12
	Bridges over SC-1
	Lump Sum
	$30,000
	2
	$60,000

	13
	Stabilized Livestock Crossing
	Lump Sum
	$3,600
	1
	$3,600

	14
	Habitat Boulders 3’
	EA
	$90.00
	16
	$1,440

	15
	Type I LWM Structures
	EA
	$10,980
	6
	$65,880

	16
	Type II LWM Structures
	EA
	$7,560
	11
	$83,160

	17
	Type III LWM Structures
	EA
	$6,600
	7
	$46,200

	18
	Type IV LWM Structures
	EA
	$16,800
	1
	$16,800

	19
	Type V LWM Structures
	EA
	$15,780
	2
	$31,560

	20
	Large Wood Material – side channel habitat
	EA
	$1,020
	20
	$20,400

	21
	Type VI LWM Structure
	Lump Sum
	$1,200
	1
	$1,200

	22
	 Live Stake – 4’
	EA
	$2.40
	3,850
	$9,240

	23
	1 Gallon Container
	EA
	$6.00
	17,280
	$103,680

	24
	Plant Protection
	EA
	$2.40
	17,280
	$41,472

	25
	Seeding (sites, access, staging )
	Acre
	$676.80
	5
	$3,384

	26
	Straw Mulch (2 ton/ac for access routes, staging)
	Ton
	$180.00
	20
	$3,600

	27
	Site cleanup and Repair
	Lump Sum
	$3,000
	1
	$3,000

	28
	USWCD construction planning, design, management
	HR
	$45.51
	502
	$22,847.20

	                                                                                                     Total Construction Costs                 $ 640,947.20


Proposed Habitat Work, R.M 44.1-44.8, Phase III, FY 2015

[image: image4.emf]Item # Item Description Units Unit Cost Quantity Cost

1 General Requirements Lump Sum 2,500 $         1 2,500 $           

2 Mobilization and Demobilization Lump Sum 30,000 $       1 30,000 $         

3 Environmental Controls (SWPPP, ESC, Etc.) Lump Sum 5,000 $         1 5,000 $           

4 Construction Staking Day 1,265 $         10 12,650 $         

5 Cofferdams, Dewatering and Water Management Lump Sum 45,000 $       1 45,000 $         

6 Temporary Haul Roads Lump Sum 5,000 $         1 5,000 $           

7 Stripping  CY 3.45 $           1000 3,450 $           

8 Floodplain Excavation CY 4.60 $           1100 5,060 $           

9 Main Channel Excavation CY 5.18 $           7000 36,225 $         

10 Side Channel Excavation CY 5.18 $           950 4,916 $           

11 Excavated Material Placed and Compacted as Fill CY 5.75 $           9050 52,038 $         

12 In-Channel Habitat Boulders Each 86 $              60 5,175 $           

13 Stabilized Livestock Crossing Each 3,450 $         2 6,900 $           

14 Fine Grading Channel and Floodplain Acre 5,750 $         2.5 14,375 $         

15 Riffle Construction Each 4,140 $         10 41,400 $         

16 Large Wood Structures  Lump Sum 389,750 $     1 389,750 $       

17 Large Wood Structures  Lump Sum 493,932 $     - $               

18 Large Wood Structures Lump Sum 120,535 $     - $               

19 Plant and Sod Salvage and Transplanting Lump Sum 1,750 $         1 1,750 $           

20 Bank Zone Planting Lump Sum 22,250 $       1 22,250 $         

21 Riparian Zone Planting Lump Sum 22,600 $       1 22,600 $         

22 Wetland Zone Planting Lump Sum 5,100 $         1 5,100 $           

23 Seeding  Lump Sum 5,350 $         1 5,350 $           

24 Straw Mulch Acre 173 $            22.2 3,830 $           

25 Site Cleanup Lump Sum 5,000 $         1 5,000 $           

26 USWCD planning, design, management HR $45.51 439 $19,979

745,309 $     



Total Construction Cost


Proposed Habitat Work, R.M 43.3-44.1, Phase IV, FY 2016

[image: image5.emf]2 Mobilization and Demobilization Lump Sum 40,000 $          1 40,000 $           

3 Environmental Controls (SWPPP, ESC, Etc.)Lump Sum 10,000 $          5 50,000 $           

4 Construction Staking Day 1,265 $            15 18,975 $           

5 Cofferdams, Dewatering  Lump Sum 30,000 $          6 180,000 $         

6 Temporary Haul Roads Lump Sum 7,500 $            5 37,500 $           

7 Stripping  CY 3.45 $              3200 11,040 $           

8 Floodplain Excavation CY 4.60 $              5000 23,000 $           

9 Main Channel Excavation CY 5.18 $              14100 72,968 $           

10 Side Channel Excavation CY 5.18 $              8000 41,400 $           

11 Excavated Material  CY 5.75 $              27100 155,825 $         

12 In-Channel Habitat Boulders Each 86 $                 120 10,350 $           

13 Stabilized Livestock Crossing Each 3,450 $            - $                 

14 Fine Grading Channel and Floodplain Acre 5,750 $            10.8 62,100 $           

15 Riffle Construction Each 4,140 $            16 66,240 $           

16 Large Wood Structures  Lump Sum 389,750 $        - $                 

17 Large Wood Structures Lump Sum 493,932 $        1 493,932 $         

18 Large Wood Structures  Lump Sum 120,535 $        - $                 

19 Plant and Sod Salvage and Transplanting Lump Sum 3,500 $            1 3,500 $             

20 Bank Zone Planting Lump Sum 29,150 $          1 29,150 $           

21 Riparian Zone Planting Lump Sum 68,250 $          1 68,250 $           

22 Wetland Zone Planting Lump Sum 6,800 $            1 6,800 $             

23 Seeding  Lump Sum 10,550 $          1 10,550 $           

24 Straw Mulch Acre 173 $               41.8 7,211 $             

25 Site Cleanup Lump Sum 7,500 $            1 7,500 $             

26 USWCD construction design, managementHR 45.51 439 19,979 $           

1,418,769 $     Total Construction Cost


Proposed Habitat Work, R.M 42.8-43.3, Phase IV, FY 2016-2017


[image: image6.emf]Item # Item Description Units Unit Cost Quantity Cost

1 General Requirements Lump Sum 2,300 $         1 2,300 $           

2 Mobilization  Lump Sum 20,000 $       1 20,000 $         

3 Environmental Controls (SWPPP, ESC, Etc.) Lump Sum 2,500 $         1 2,500 $           

4 Construction Staking Day 1,265 $         5 6,325 $           

5 Cofferdams, Dewatering  Lump Sum 20,000 $       1 20,000 $         

6 Temporary Haul Roads Lump Sum 5,000 $         1 5,000 $           

7 Stripping  CY 3.45 $           1500 5,175 $           

8 Floodplain Excavation CY 4.60 $           2500 11,500 $         

9 Main Channel Excavation CY 5.18 $           1700 8,798 $           

10 Side Channel Excavation CY 5.18 $           - $               

11 Excavated Material  CY 5.75 $           4200 24,150 $         

12 In-Channel Habitat Boulders Each 86 $              30 2,588 $           

13 Stabilized Livestock Crossing Each 3,450 $         2 6,900 $           

14 Fine Grading Channel and Floodplain Acre 5,750 $         3.2 18,400 $         

15 Riffle Construction Each 4,140 $         2 8,280 $           

16 Large Wood Structures  Lump Sum 389,750 $     - $               

17 Large Wood Structures  Lump Sum 493,932 $     - $               

18 Large Wood Structures  Lump Sum 120,535 $     1 120,535 $       

19 Plant and Sod Salvage  Lump Sum 1,725 $         1 1,725 $           

20 Bank Zone Planting Lump Sum 15,350 $       1 15,350 $         

21 Riparian Zone Planting Lump Sum 9,400 $         1 9,400 $           

22 Wetland Zone Planting Lump Sum 850 $            1 850 $              

23 Seeding  Lump Sum 2,300 $         1 2,300 $           

24 Straw Mulch Acre 173 $            9.2 1,587 $           

25 Site Cleanup Lump Sum 2,500 $         1 2,500 $           

26 USWCD construction design, management HR 45.51 124 5,643 $           

301,805 $      Total Construction Cost


TOTAL Budget – All Phases/Years:

	Consolidated Intake Structure
	$205,000

	Irrigation Pipeline
	$270,500

	Habitat
	$3,106,830.20


9.  Attachments: Please see attachments including project maps, design, photos. 

Sheet1



		Item #		Item Description		Units		Unit Cost		Quantity		Cost

		1		General Requirements		Lump Sum		$   2,500		1		$   2,500

		2		Mobilization and Demobilization		Lump Sum		$   30,000		1		$   30,000

		3		Environmental Controls (SWPPP, ESC, Etc.)		Lump Sum		$   5,000		1		$   5,000

		4		Construction Staking		Day		$   1,265		10		$   12,650

		5		Cofferdams, Dewatering and Water Management		Lump Sum		$   45,000		1		$   45,000

		6		Temporary Haul Roads		Lump Sum		$   5,000		1		$   5,000

		7		Stripping 		CY		$   3.45		1000		$   3,450

		8		Floodplain Excavation		CY		$   4.60		1100		$   5,060

		9		Main Channel Excavation		CY		$   5.18		7000		$   36,225

		10		Side Channel Excavation		CY		$   5.18		950		$   4,916

		11		Excavated Material Placed and Compacted as Fill		CY		$   5.75		9050		$   52,038

		12		In-Channel Habitat Boulders		Each		$   86		60		$   5,175

		13		Stabilized Livestock Crossing		Each		$   3,450		2		$   6,900

		14		Fine Grading Channel and Floodplain		Acre		$   5,750		2.5		$   14,375

		15		Riffle Construction		Each		$   4,140		10		$   41,400

		16		Large Wood Structures 		Lump Sum		$   389,750		1		$   389,750

		17		Large Wood Structures 		Lump Sum		$   493,932				$   - 0

		18		Large Wood Structures		Lump Sum		$   120,535				$   - 0

		19		Plant and Sod Salvage and Transplanting		Lump Sum		$   1,750		1		$   1,750

		20		Bank Zone Planting		Lump Sum		$   22,250		1		$   22,250

		21		Riparian Zone Planting		Lump Sum		$   22,600		1		$   22,600

		22		Wetland Zone Planting		Lump Sum		$   5,100		1		$   5,100

		23		Seeding 		Lump Sum		$   5,350		1		$   5,350

		24		Straw Mulch		Acre		$   173		22.2		$   3,830

		25		Site Cleanup		Lump Sum		$   5,000		1		$   5,000

		26		USWCD planning, design, management		HR		$45.51		439		$19,979

		Total Construction Cost										$   745,309




















Sheet1

		Item #		Item Description		Units		Unit Cost		Quantity		Cost

		1		General Requirements		Lump Sum		$   2,500		1		$   2,500

		2		Mobilization and Demobilization		Lump Sum		$   40,000		1		$   40,000

		3		Environmental Controls (SWPPP, ESC, Etc.)		Lump Sum		$   10,000		5		$   50,000

		4		Construction Staking		Day		$   1,265		15		$   18,975

		5		Cofferdams, Dewatering 		Lump Sum		$   30,000		6		$   180,000

		6		Temporary Haul Roads		Lump Sum		$   7,500		5		$   37,500

		7		Stripping 		CY		$   3.45		3200		$   11,040

		8		Floodplain Excavation		CY		$   4.60		5000		$   23,000

		9		Main Channel Excavation		CY		$   5.18		14100		$   72,968

		10		Side Channel Excavation		CY		$   5.18		8000		$   41,400

		11		Excavated Material 		CY		$   5.75		27100		$   155,825

		12		In-Channel Habitat Boulders		Each		$   86		120		$   10,350

		13		Stabilized Livestock Crossing		Each		$   3,450				$   - 0

		14		Fine Grading Channel and Floodplain		Acre		$   5,750		10.8		$   62,100

		15		Riffle Construction		Each		$   4,140		16		$   66,240

		16		Large Wood Structures 		Lump Sum		$   389,750				$   - 0

		17		Large Wood Structures		Lump Sum		$   493,932		1		$   493,932

		18		Large Wood Structures 		Lump Sum		$   120,535				$   - 0

		19		Plant and Sod Salvage and Transplanting		Lump Sum		$   3,500		1		$   3,500

		20		Bank Zone Planting		Lump Sum		$   29,150		1		$   29,150

		21		Riparian Zone Planting		Lump Sum		$   68,250		1		$   68,250

		22		Wetland Zone Planting		Lump Sum		$   6,800		1		$   6,800

		23		Seeding 		Lump Sum		$   10,550		1		$   10,550

		24		Straw Mulch		Acre		$   173		41.8		$   7,210

		25		Site Cleanup		Lump Sum		$   7,500		1		$   7,500

		26		USWCD construction design, management		HR		45.51		439		$   19,979

		Total Construction Cost										$   1,418,769






Sheet1

		Item #		Item Description		Units		Unit Cost		Quantity		Cost

		1		General Requirements		Lump Sum		$   2,300		1		$   2,300

		2		Mobilization 		Lump Sum		$   20,000		1		$   20,000

		3		Environmental Controls (SWPPP, ESC, Etc.)		Lump Sum		$   2,500		1		$   2,500

		4		Construction Staking		Day		$   1,265		5		$   6,325

		5		Cofferdams, Dewatering 		Lump Sum		$   20,000		1		$   20,000

		6		Temporary Haul Roads		Lump Sum		$   5,000		1		$   5,000

		7		Stripping 		CY		$   3.45		1500		$   5,175

		8		Floodplain Excavation		CY		$   4.60		2500		$   11,500

		9		Main Channel Excavation		CY		$   5.18		1700		$   8,798

		10		Side Channel Excavation		CY		$   5.18				$   - 0

		11		Excavated Material 		CY		$   5.75		4200		$   24,150

		12		In-Channel Habitat Boulders		Each		$   86		30		$   2,588

		13		Stabilized Livestock Crossing		Each		$   3,450		2		$   6,900

		14		Fine Grading Channel and Floodplain		Acre		$   5,750		3.2		$   18,400

		15		Riffle Construction		Each		$   4,140		2		$   8,280

		16		Large Wood Structures 		Lump Sum		$   389,750				$   - 0

		17		Large Wood Structures 		Lump Sum		$   493,932				$   - 0

		18		Large Wood Structures 		Lump Sum		$   120,535		1		$   120,535

		19		Plant and Sod Salvage 		Lump Sum		$   1,725		1		$   1,725

		20		Bank Zone Planting		Lump Sum		$   15,350		1		$   15,350

		21		Riparian Zone Planting		Lump Sum		$   9,400		1		$   9,400

		22		Wetland Zone Planting		Lump Sum		$   850		1		$   850

		23		Seeding 		Lump Sum		$   2,300		1		$   2,300

		24		Straw Mulch		Acre		$   173		9.2		$   1,587

		25		Site Cleanup		Lump Sum		$   2,500		1		$   2,500

		26		USWCD construction design, management		HR		45.51		124		$   5,643

		Total Construction Cost										$   301,805






Sheet1





		Qty		Description		Unit		Materials		Labor		Total Incl. O&P		Cost

		1		Mob and Demobilization		LS								$22,353.52

		1		Clear and grub		LS						$4,000.00		$4,000.00

		500		15" PVC-PIP		L.F.		$10.60		$4.20		$14.80		$7,400.00

		6440		10" PVC-PIP		L.F.		$4.70		$3.50		$8.20		$52,808.00

		1102		8" PVC-PIP		L.F.		$3.00		$2.00		$5.00		$5,510.00

		3495		6" PVC-PIP		L.F.		$1.70		$1.00		$2.70		$9,436.50

		3219		4" PVC-PIP		L.F.		$0.80		$0.50		$1.30		$4,184.70

		7500		Excavation & Backfill		C.Y.		$9.60		$2.40		$12.00		$90,000.00

		550		Select Backfill for Pipe Bedding		C.Y.		$33.60		$8.40		$42.00		$23,100.00

		5		4" Farm Delivery		Ea.		$2,000.00		$1,500.00		$3,500.00		$17,500.00

		23		Turnouts (Alfalfa Valve)		Ea.		$120.00		$30.00		$150.00		$3,450.00

		2		Turbulent Fountain Screen		Ea.		$1,947.00		$1,126.00		$3,073.00		$6,146.00

								Total for listed items						$245,888.72

								Unlisted Items				10%		$24,588.87

								Total for Schedule						$270,477.59



								TOTAL CONSTRUCTION COST						$270,500.00






