## Budget
1992-026-01 – Grande Ronde Model Watershed Wallowa Green Valley Ranch Fish Passage 2022 Subcontractor Budget September 1, 2022 - December 31, 2023 CR 357335
WE | Construction | Qty | Unit | Unit Cost | Total
C,D | Mobilization and Demobilization | 1 | LS | 22500 | 22500
C,D | Environmental Controls (SWPPP, hydraulic fluids, etc.) | 1 | LS | 6250 | 6250
B,C,D | Environmental Protections | 1 | LS | 3750 | 3750
C,D | Cofferdam, Diversions, Dewatering and Water Management | 1 | EA | 6250 | 6250
C,D | Removal of structures (existing irrigation dam, pump sump) | 1 | EA | 6250 | 6250
C,D | Clearing, grubbing, stockpile, and disposal | 0.5 | ACRES | 7500 | 3750
C,D | General excavation (Excavation and stockpile) | 170 | EA | 25 | 4250
C,D | Fill in place (Stockpiled material) | 210 | CY | 63 | 13230
C | Fill in place (Imported streambed sediment) | 240 | CY | 125 | 30000
C | Fill in place (Imported habitat boulders for boulder clusters) | 40 | CY | 125 | 5000
D | Install LWM Structure-Bank Rootwads | 1 | EA | 9875 | 9875
D | Install LWM Structure-Floodplain roughness logs | 12 | EA | 2000 | 24000
C | Headgate and headwall | 1 | LS | 25000 | 25000
C | Relocate existing irrigation surface pump | 1 | LS | 2500 | 2500
E | Seed and Mulch | 0.5 | ACRES | 6250 | 3125
E | Planting | 0.5 | ACRES | 3125 | 1562.5
C,D | Construction staking | 3 | DAY | 1365 | 4095
C,D | Construction observation | 4 | DAY | 2000 | 8000
| Sub-Contract Budget Total |  |  |  | 179387.5
Note: GRMW will administer the subcontract for ODFW, there will be no indirect applied, GRMW indirect for this will come out of the GRMW Admin contract