## Summary
Item | Unit Type | Unit Number | Unit Cost | OWEB Funds | BPA Funds | External In-Kind | Total Costs
Project Management
NPT NEOR/SEWA Project Leader | Hours | 80 | 45 |  |  | 3600 | 3600
NPT NEOR/SEWA Specialist I | Hours | 80 | 35 |  |  | 2800 | 2800
NPT Watershed Deputy Director - Contract Management | Hours | 60 | 60 |  |  | 3600 | 3600
NPT Staff Project Observation | Hours | 40 | 45 |  |  | 1800
GRMW Staff Project Observation, technical assistance | Hours | 40 | 45 |  |  | 1800
Contracted Services
Mobilization | Each | 1 | 12000 | 12000 |  |  | 12000
Clearing and Grubbing & Site Preparation | Hours | 40 | 200 | 8000 |  |  | 8000
Work areas isolation and water management | Hours | 30 | 250 | 7500 |  |  | 7500
Project Elements
LWD SC Intake structures (4 structures) - Materials (see sheet6) | Each | 4 | 5120 |  | 20480 |  | 20480
Labor to Construct (8 hours / structure) | Hours | 32 | 200 |  | 6400 |  | 6400
LWD Alcove 1- Materials (2 LWM structures) | Each | 1 | 6400 |  | 6400 |  | 6400
Labor to Construct Alcove 1 | Hours | 8 | 200 |  | 1600 |  | 1600
LWD Alcove 2- Materials (1 LWM structure) | Each | 1 | 4000 |  | 4000 |  | 4000
Labor to Construct | Hours | 8 | 200 |  | 1600 |  | 1600
Side Channel Whole Tree Placement- Materials | Each | 20 | 800 | 16000 |  |  | 16000
Labor to Construct (total whole trees) | Hours | 40 | 200 | 8000 |  |  | 8000
Side Channel Network - Floodplain Excavation | Cubic yards | 8100 | 8 |  | 64800 |  | 64800
Side Channel Network - Substrate - Bed Material | Cubic yards | 3199.601 | 8 |  | 25597 |  | 25597
Labor to Construct (hauling, screening and placement) | Hours | 40 | 250 | 10000 |  |  | 10000
Side Channel Network - Brush - Bankline Treatment- Materials | Feet | 2587.5403 | 15 | 38813.1045 |  |  | 38813.1045
Labor to Construct (See sheet 10) | Hours | 80 | 150 | 12000 |  |  | 12000
Side Channel Network - Large Substrate Placement- Materials | Each | 1 | 50500 |  | 50500 |  | 50500
Labor to Construct | Hours | 60 | 150 | 9000 |  |  | 9000
Main-Stem Boulder Placements- Materials | Each | 5 | 4100 |  | 20500 |  | 20500
Labor to Construct | Hours | 8 | 200 |  | 1600 |  | 1600
Miscellaneous Wood (side channels and floodplain)- Materials | Each | 1 | 9000 | 9000 |  |  | 9000
Labor to Construct | Hours | 20 | 200 | 4000 |  |  | 4000
Constructed Wetlands (4 sites - acre) | Hours | 30 | 200 | 6000 |  |  | 6000
Floodplain Roughness | Hours | 30 | 201 | 6030 |  |  | 6030
Ditch plugs | Each | 8 | 1200 | 9600 |  |  | 9600
Site Restoration | Hours | 40 | 200 | 8000 |  |  | 8000
Willow Clump Plantings | Each | 400 | 20 | 8000 |  |  | 8000
Additional Willow Cuttings | Each | 2000 | 5 | 10000 |  |  | 10000
Willow Cutting installation (NPT staff) | Hours | 80 | 40 |  |  | 3200
Seeding (20 lbs/ac for 3 ac) | Each | 6 | 15 | 90 |  |  | 90
Site Cleanup - Restoration | Hours | 20 | 200 | 4000 |  |  | 4000
Total |  |  |  | 186033.1045 | 203477 | 16800 | 406310.1045
Contigency ( 10% project total minus in kind) | [6 empty] | 38951
Project Total | [6 empty] | 445261.1045

## Calcs
Item | Unit Type | Unit Number | Unit Cost | OWEB Funds | External Cash | External In-Kind | Total Costs
Contracted Services | [14 empty] | LWD ($800/tree 2 ft dbh whole tree with rootwad
Mobilization | Each | 1 | 12000 | 12000 | 0 | 0 | 12000 | [7 empty] | each | # Tree /STR | $/STR | # STR | Total
Clearing and Grubbing & Site Preparation | Hours | 40 | 200 | 8000 | 0 | 0 | 8000 | [7 empty] | 800 | 6 | 4800 | 4 | 19200
Work areas isolation and water management | Hours | 30 | 250 | 7500 | 0 | 0 | 7500 | [7 empty] | Slash (m assume 10 cuyds / load
Project Elements | [14 empty] | Load | Loads/STR | $/STR | # STR | Total
LWD SC Intake structures (4 structures) - Materials | Each | 4 | 5120 | 20480 | 0 | 0 | 20480 | 5120 | [6 empty] | 160 | 2 | 320 | 4 | 1280
Labor to Construct (8 hours / structure) | Hours | 32 | 200 | 6400 |  |  | 6400 | [8 empty] | Labor (1 str /day $160/hr @ 8 hours) | $/STR | # STR | Total
LWD Alcove 1- Materials | Each | 1 | 6400 | 6400 | 0 | 0 | 6400 | 6400 | [8 empty] | 1280 | 4 | 5120
Labor to Construct | Hours | 8 | 200 | 1600 |  |  | 1600
LWD Alcove 2- Materials | Each | 1 | 4000 | 4000 | 0 | 0 | 4000 | 4000 | [10 empty] | Total
Labor to Construct | Hours | 8 | 200 | 1600 |  |  | 1600 | [7 empty] | Additional Whole Trees Alcove 1 | 8 | 800 |  | 6400
Side Channel Whole Tree Placement- Materials | Each | 20 | 800 | 16000 | 0 | 0 | 16000 | 12800 | [6 empty] | Additional Whole Trees Alcove 2 | 5 | 800 |  | 4000
Labor to Construct (total whole trees) | Hours | 40 | 200 | 8000 |  |  | 8000 |  |  | 3625 |  |  |  |  | Additional Whole Trees SC | 16 | 800 |  | 12800
Side Channel Network - Floodplain Excavation | Cubic yards | 8100 | 10 | 81000 | 0 | 0 | 81000 | 47772 | [8 empty] | 9$/cuyd
Side Channel Network - Substrate - Bed Material | Cubic yards | 3199.601 | 10 | 31996.0099 | 0 | 0 | 31996.0099 | [6 empty] | Side channel network excavation |  | 5308 | 9 |  | 47772
Labor to Construct (hauling, screening and placement) | Hours | 40 | 250 | 10000 | 0 | 0 | 10000 | 31996.0099 | [5 empty] | over excavation |  | 3199.601
Side Channel Network - Brush - Bankline Treatment- Materials | Feet | 2587.5403 | 15 | 38813.1045 | 0 | 0 | 38813.1045
Labor to Construct | Hours | 80 | 150 | 12000 | 0 | 0 | 12000 | 15870.2472
Side Channel Network - Large Substrate Placement- Materials | Each | 1 | 50500 | 50500 | 0 | 0 | 70700 | [8 empty] | $/bldr | # sites | # Bldrs | Total
Labor to Construct | Hours | 60 | 150 | 9000 |  |  | 9000 | 70700 | [6 empty] | 3.5' MEAN DIA. BOULDERS | 75 | 5 | 25 | 9375 |  | 400
Main-Stem Boulder Placements- Materials | Each | 5 | 4100 | 20500 | 0 | 0 | 20500 | [7 empty] | 2.5' MEAN DIA. BOULDERS | 50 | 5 | 35 | 8750
Labor to Construct | Hours | 8 | 200 | 1600 |  |  | 1600 | 18125 |  | 3625
Miscellaneous Wood (side channels and floodplain)- Materials | Each | 1 | 9000 | 9000 | 0 | 0 | 9000 | [8 empty] | Area SQ.ft | substrate | $/cuyd | Total
Labor to Construct | Hours | 20 | 200 | 4000 |  |  | 4000 | [7 empty] | SC Footprint | 43194.6133 | 3199.601 | 10 | 31996.0099
Constructed Wetlands (4 sites - acre) | Hours | 30 | 200 | 6000 |  |  | 6000 | [8 empty] | Area SQ.ft
Floodplain Roughness | Hours | 30 | 201 | 6030 |  |  | 6030
Ditch plugs | Each | 8 | 1200 | 9600 |  |  | 9600 | [7 empty] | 3.5' MEAN DIA. BOULDERS | 75
Site Restoration | Hours | 40 | 200 | 8000 | 0 | 0 | 8000 |  |  |  | *350 placed for 3 |  |  |  | 2.5' MEAN DIA. BOULDERS | 50
Willow Clump Plantings | Each | 400 | 20 | 8000 | 0 | 0 | 8000
Additional Willow Cuttings | Each | 2000 | 5 | 10000 | 0 | 0 | 10000 | [8 empty] | ft | 0.35 | $ 3.5' | $ 2.5'
Seeding (20 lbs/ac for 3 ac) | Each | 6 | 15 | 90 | 0 | 0 | 90
Site Cleanup - Restoration | Hours | 20 | 200 | 4000 | 0 | 0 | 4000 |  | 350 | 800 | 280000 |  |  |  | SC1 length | 1082 | 378.7 | 28402.5 | 18935
Total | [6 empty] | 432309.1144 |  |  |  | 210000 |  |  |  | SC2 length | 224 | 78.4 | 5880 | 3920
Contigency (Total + 10%) | [6 empty] | 475540.0258 | [7 empty] | SC3 length | 310 | 108.5 | 8137.5 | 5425
[17 empty] | Total | 42420 | 28280
wetland acreage
[8 empty] | 2 and 2 |  | 2588 | 6.47
Bankline Brush Treatment
[16 empty] | Bank Length | 2587.5403
Treatment | Treatment Explanation | Description | Unit Cost | Units | Quantity
BR-A | Excavate river | Cut | 13 | cubic yards | 40000 | [11 empty] | # | 5$/cutting
BR-B | Construct floodplain | Fill/grading | 10 | cubic yards | 40000 | [9 empty] | Willow Cuttings (1/.8lf) |  | 2070.0322 | 10350.1612 |  | 15870.2472
BR-C | Enhance wetlands | Emergent wetland reveg | 39952 | acres | 8 | [12 empty] | 160/10 cuyds |  | 6.1333
BR-D | Enhance side channels | Structures/grading/reveg | 63 | feet | 3800 | [10 empty] | Bankline Brush .8 foot thick 4 ft long) | 345.0054 | 5520.086
BR-E | Revegetation | Planting/microtopography | 39952 | acres | 2.5
BR-F1 | Bank structures | Bioengineering | 267 | feet | 3600
BR-F2 | Bank structures | Lower bank restoration | 267 | feet | 1300 | [9 empty] | Willow Clumps |  | 172.5027
BR-F3 | Bank structures | LWD habitat | 20000 | structures | 22
BR-G1 | In-stream structures | Pool formation | 119413 | structures | 4
BR-G2 | In-stream structures | Substrate mat | 119413 | structures
MR-J | Tributary restoration | Cow Creek | 63 | feet | [10 empty] | Constructed Wetlands
KR-C | Manage land use | Exclosure fencing | 10 | feet | 6400 | [10 empty] | 6907.48
KR-D1 | Mitigate infrastruture | Culvert replacement | 600 | feet | [11 empty] | 9991.4669
KR-D2 | Mitigate infrastruture | Bank rehabilitation | 267 | feet | [11 empty] | 8052.5148
16391.4315
Estimated Quantities | [14 empty] | Acres | 41342.8932
Site 1
ELWS A
Large wood members | 6 logs w/6' effective rootwad, 2' min dia., 25 - 30' stem length
Slash | 15 tops or large branches, 6" stem dia., 10 foot length
Boulder ballast | 2, 5' mean dia. boulders
4, 4' mean dia. boulders
10, 4' long, 1" dia. rebar pins
ELWS B
Large wood members | 10 logs w/6' effective rootwad, 2' min dia., 25 - 30' stem length
Slash | 25 tops or large branches, 6" steam dia., 10 foot length
Boulder ballast | 6, 5' mean dia. boulders
15, 4' long, 1" dia. rebar pins
Site 2
ELWS
Large wood members | 13 logs w/6' effective rootwad, 2' min dia., 25 - 30' stem length
Slash | 15 tops or large branches, 6" steam dia., 10 foot length
Boulder ballast | 4, 5' mean dia. boulders
5, 3.5' mean dia. boulders
20, 4' long, 1" dia. rebar pins
Site 3
ELWS
Large wood members | 7 logs w/6' effective rootwad, 2' min dia., 25 - 30' stem length
Slash | 25 tops or large branches, 6" steam dia., 10 foot length
Riffle
Matrix gradation | 60 cu.yds. | [10 empty] | Cost/#
Roughness Elements | 10, 5' dia. boulders | [8 empty] | #/Structure | Total # | 500 | Cost
| 12, 4.5' dia. boulders | [8 empty] | 27 | 27 | 250 | 13500
| 20, 3.5' dia. boulders | [8 empty] | 111 | 111 | 125 | 27750
[10 empty] | 125 | 125 |  | 15625
Pool | [10 empty] | 263 | 10
Excavation | 250 cu.yds. | [8 empty] | 875 | 875 | 100 | 8750
[10 empty] | 120 | 120 | 75 | 12000
Side Channel | [9 empty] | 60 | 60 | 10 | 4500
Excavation | 1500 cu.yds. | [8 empty] | 300 | 300 |  | 3000
Slash | 30 tops or large branches, 6" steam dia., 10 foot length | [10 empty] | Total =
85125
Cost/#
MIDCHANNEL ELSW (1) | [9 empty] | #/Structure | Total # | 100 | Cost
[10 empty] | 10 | 30 | 75 | 3000
LARGE WOOD MEMBERS LOGS W/6' EFFECTIVE ROOTWAD, 2' MIN DIA., 30 - 35' STEM LENGTH | [9 empty] | 20 | 60 | 50 | 4500
| LOGS, 1.5' MIN DIA., 25-30' STEM LENGTH | [8 empty] | 30 | 90 | Total = | 4500
| LOGS, 1' MIN DIA., 25-30' STEM LENGTH | [11 empty] | 12000
Total Material Cost For Upper Miller Quarry Reach
SLASH TOPS OR LARGE BRANCHES, 6" STEM DIA., 10 FOOT LENGTH (Cubic Yards) | [12 empty] | 97125
BOULDER BALLAST 5' MEAN DIA. BOULDERS
4' MEAN DIA. BOULDERS
4' LONG, 1.27" DIA. (#10) REBAR PINS
REVEGETATION
DBRE DISTRIBUTED BOULDER PLACEMENT (3)
4.5' MEAN DIA. BOULDERS
3.5' MEAN DIA. BOULDERS
2.5' MEAN DIA. BOULDERS