Project Information:

Project Name:	Bear Creek Sauvage Fish Habitat Restoration

Proposed Implementation:	Month, Year

BPA Project #:	1992-026-01

Contract #:	90768 REL 7

Sponsor:	Grand Ronde & Umatilla Fish Habitat Improvement Project

Designer:	Applied Science and Engineering

Area Lead:	Dropdown Menu

COR/PM:	Tracy Hauser

HIP Review Team:

HIP Program Lead:	Daniel A. Gambetta, ECF

BPA EC Lead:	Lindsey Arotin

BPA Technical Lead:	Mike Ward, P.E. EWL

NMFS Branch Chief:	Bill Lind, NMFS, Southern Snake Branch Chief

NMFS Biologist:	Jim Morrow

NMFS Engineer:	Dropdown Menu

USFWS Field Office:	Marisa Meyers, USFWS La Grande Field Office

USFWS Reviewer:	Graham Shaw

Documents Reviewed:

Bear Creek Sauvage Fish Habitat Restoration Project 15%                        January 27, 2025

Document 2

Document 3

Activity Categories:	Risk Level:

2a - Improve Secondary Channel and Floodplain Connectivity	High

2d - Install Habitat-Forming Instream Structures	Medium

2e - Riparian and Wetland Vegetation Planting	Low

1g - Bridge and Culvert Maintenance	Low

Dropdown Menu	Dropdown Menu

Dropdown Menu	Dropdown Menu

Dropdown Menu	Dropdown Menu

Dropdown Menu	Dropdown Menu

Overall Project Risk	High

Review Timeline:	Date Completed

- Conceptual Review (typically 15%)

  - Site visit, if needed	Not Started

  - Sponsor to submit conceptual design to EC Lead and COR	1/27/2025

  - EC Lead to submit concept to HIP Review Team to initiate review	1/27/2025

  - EC Lead to send design package to appropriate HIP Review members	1/27/2025

  - EC Lead to compile comments and forward to Sponsor	4/2/2025

  - Sponsor to provide responses to EC Lead	Not Started

  - HIP Review Team and Sponsor to resolve “open” comments	Not Started

  - EC Lead to notify Sponsor to proceed to preliminary design	Not Started

- Preliminary Design or Alternatives Analysis Review (typically 30%)

  - Sponsor to submit preliminary design to EC Lead and COR	Not Started

  - EC Lead to submit design package to HIP Review Team	Not Started

  - EC Lead to submit design to NMFS Engineer if applicable	Not Started

  - NMFS Engineer approves project, if applicable	Not Started

  - EC Lead to compile comments and forward to Sponsor	Not Started

  - Sponsor to provide responses to EC Lead	Not Started

  - HIP Review Team and Sponsor to resolve “open” comments	Not Started

  - EC Lead to notify Sponsor to proceed with design	Not Started

- Permit Level Design Review (typically 60% to 80%)

  - Sponsor to submit design package to EC lead and COR	Not Started

  - EC Lead to submit design package to HIP Review Team	Not Started

  - EC Lead to compile comments and forward to Sponsor	Not Started

  - Sponsor to provide responses to EC Lead	Not Started

  - HIP Review Team and Sponsor to resolve “open” comments	Not Started

  - EC Lead to notify Sponsor to proceed to final design	Not Started

- Final Design Package (100%)

  - Sponsor to submit final designs to EC Lead and COR	Not Started

  - EC Lead and BPA Technical Lead to verify no critical changes	Not Started

Comments:

| # | Reviewer (Org.) | Date | Document | Page/ Section | Comment |  | Response by (Org.) | Date | Response to Comment | Status (BPA to Update) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BPA | 4/1/25 | 15% General | NA | Please provide a cost estimate and cost benefit analysis for the proposed bridge and culverts at the next submittal. |  | ODFW | 4/8/2025 | Acknowledged, will be addressed at 30% | To be Addressed at Next Review |
|  | BPA | 4/1/25 | 15% General | NA | Please provide area of potential effect (APE) map shapefiles for the cultural resource consultation. APE maps should include any additional information pertaining to project activities (e.g. access roads, staging areas, vegetation planting etc. |  | ODFW | 4/8/2025 | Acknowledged, will be addressed at 30%. | To be Addressed at Next Review |
|  | BPA | 4/1/25 | 15% General | NA | Please ensure wetlands, the Ordinary High Water (OHW) line, and FEMA 100- year floodplain boundary are included on all plan sheets. |  | ODFW | 4/8/2025 | Acknowledged, will be addressed at 30% | To be Addressed at Next Review |
|  | BPA | 4/1/25 | 15% General | NA | In the 30%, please show all access roads, staging, storage, and stockpile areas that would be used for equipment and construction materials. Keep these areas 150 feet or more from natural waterbodies and wetlands or on an adjacent established road area in a location and manner that will preclude erosion into, or contamination of, the stream or floodplain. Staging areas may be closer than 150 feet if the area is above (elevation) the 100-yr floodplain and spill prevention measures are approved by BPA. |  | ODFW | 4/8/2025 | Acknowledged, will be addressed at 30% | To be Addressed at Next Review |
|  | USFWS | 03/12/2025 | 15% General | NA | Mussel presence in Bear Creek is unknown, but it is suspected that western pearlshell may be present. We recommend that surveys be conducted to confirm and results be reported to the Xerces Society (emilie.blevins@xerces.org) and please CC USFWS. |  | ODFW | 4/8/2025 | Acknowledged, mussel survey will be conducted and reported summer 2025. | Dropdown Menu |
|  | USFWS | 03/12/2025 | 15% General | NA | What have the conversations been with ODFW District regarding brook trout? Do these designs reflect the District input/concerns with brook trout? Do the District’s removal efforts factor into the timeline for implementation? |  | ODFW | 4/8/2025 | As discussed, ODFW Fish Habitat and District staff will remain in conversation. District does not seem concerned with design but is requesting post-monitoring of side channels for brook trout after construction which we will conduct with them. | Dropdown Menu |
|  | USFWS | 03/12/2025 | 15% General | NA | Have bull trout spawning surveys been conducted within this project reach? If not, will surveys be conducted prior to implementation and what are the plans for post-project bull trout monitoring? |  | ODFW | 4/8/2025 | Yes, Mike Meeuwig and staff has conducted them in 2023. Post-project bull trout monitoring will be conducted again sometime after implementation. This also aligns with District brook trout removal efforts. | Dropdown Menu |
|  | USFWS | 03/12/2025 | 15% General | 10 & 11 | I am concerned the culvert could be insufficient if there is a rain on snow event. What type of culvert will be used? What flood return interval is it being designed for? |  | ODFW | 4/8/2025 | These alternatives will have continued discussion, a bridge or 2 bridges will contain the main flows, additional culverts will be designed for high flow relief and be appropriately sized based on the hydraulic model. Design is for predicted 100-yr flood. | Dropdown Menu |
|  | USFWS | 03/12/2025 | 15% General | 10 | Has strear stress been calculated for the proposed main channel within the cut bend. I worry that the channelized creek flowing into such as sharp bend could cause unintended erosion and add sediment to the lower sections of this project. Sorry for the random questions just wanted to check. |  | ODFW | 4/8/2025 | Acknowledged, shear stress and velocity will be included in the next design phase. This will also help to address this alternative and the concern. | Dropdown Menu |
|  | USFWS | 03/12/2025 | 15% General | 12 | On the far right side of the design there is a seasonal high flow channel that appears it will be cut off by fill pacement. Is this intentional or just the way it is dawn? Why are you trying to reduce the flow in the two seasonal high flow paths? |  | ODFW | 4/8/2025 | The current channel is straightened with little activation of the side channels, the idea was to allow the channel to meander to have more water to activate the seasonal high flow paths while also causing scour and deposition downstream for spawning. | Dropdown Menu |
|  | USFWS | 03/12/2025 | 15% General | 12 | Are you worried about the high quality habitat pool becoming filled in with sediement? The way the designs look it appears the plan is to divert the main channel to river left. The tight turn could cause water to slowdown and drop sediment. |  | ODFW | 4/8/2025 | This could be possible; however, the idea was to continue the turn in this location instead of going back to a straightened channel. The hope is to create more turns to mimic the complexity and cause scour and deposition for spawning conditions, but we can discuss this further at next phase. | Dropdown Menu |
|  | USFWS | 03/12/2025 | 15% General | NA | Looks like a great project! Excited to see it to fruition! |  |  |  |  | Dropdown Menu |